## Sheet1
Week | Task | Duration (Days) | Total Hours (Team) | Deliverables
1 | Define Scope & Assign Roles | 2 | 10 | Project Plan, Roles Assigned
1 | Data Collection & Cleaning | 2 | 10 | Cleaned Dataset
1 | EDA & Initial Visualizations | 2 | 10 | EDA Report & Preliminary Charts
2 | Set Up Dashboard Framework | 2 | 10 | Dashboard Structure
2 | Implement Core Visualizations | 2 | 10 | Interactive Charts & Filters
2 | Data Drill-Down & Interactivity | 2 | 10 | Drill-down & Time-series Analysis
3 | Design ML Model (Optional) | 2 | 10 | Trained ML Model
3 | Build & Deploy API | 2 | 10 | Deployed API
3 | Integrate API with Dashboard | 2 | 10 | Integrated API with Dashboard
4 | Debugging & Testing | 2 | 10 | Bug-free Dashboard
4 | Documentation | 2 | 10 | Complete Documentation
4 | Deployment & Final Review | 2 | 10 | Deployed Dashboard & Final Report